NACCHO CHA/CHIP GRANT WORKPLAN

Community Health Improvement PROCESS

Preparation

| Who? | What? | By When? |
| --- | --- | --- |
| Robin | Go through NACCHO notebook | 8/12/11 |
| Robin | Finalize contract | 8/12/11 |
| Robin | Finish work plan | 8/12/11 |
| Robin/Sarah/ Maria | Meet with CWU to discuss involvement | 8/29/11 |
| Robin | Research Look at other CHAs and CHIPs Review MAPP more thoroughly COPHP community assessment work? Adjust work plan to match MAPP Go through web links in NACCHO task list Look at MAPP and other models (Association for Comm. Health Improvement, PACE EH, APEX-PH, map-it, MATCH) WA state PHIP, I-plan Illinois NACCHO Health Equity tool kit, LHD National Coalition for Health Equity Quality planning National prevention strategy: Americans Plan for Better Health and Wellness, DOH Health Data Guidelines | 8/31/11 |
| Robin | Choose resources for Sarah to look at, prior webinars | 8/31/11 |
| Robin | Create plan for community engagement | 8/31/11 |
| Robin | Finalize MOU with CWU | 9/30/11 |

Community Health Assessment (CHA)

| Who? | What? | By When? |
| --- | --- | --- |
| Robin Robin/Sarah Robin Robin Robin Robin | Community Engagement Establish steering committee Schedule individual meetings with participants Put together draft charter Schedule first and subsequent meetings (kick off meeting?) Develop agenda for first meeting Report progress at BOH/BOHAC Use meeting evaluations Develop evaluation Develop draft of meeting schedule for 2012 Circle of engagement? Review quality planning/QI tools to use? | 11/30/11 Ongoing 11/20/11 Ongoing Ongoing 11/30/11 11/30/11 |
| Steering | Readiness checklist | 11/30/11 |
| Steering | Visioning process Collect ideas from staff, BOH, BOHAC, and unnatural causes event Compile for steering committee meeting Decide on visioning process for meeting Finalize Vision Add to all materials and agendas | 11/30/11 11/23/11 11/29/11 11/23/11 11/30/11 Ongoing |
| Steering | Create list of indicators Collect indicator resources (HP2020, Health Indicator Warehouse, PHIP, KHI, etc.) Find out who has access to what data | 12/9/11 |
| Steering | Select indicators Decide how to collect community input on indicators Final selection | 12/31/11 |
| Robin | Collect secondary data | 1/31/12 |
| Robin Sarah Steering CWU | Collect primary data Key informants Community surveys Focus groups | 2/28/12 |
| Robin | Data analysis/synthesis | 3/31/12 |
| Robin | Write community health profile | 5/31/12 |
| Robin Sarah Steering | Distribute community health profile Printing Distribution plan | 6/30/12 |

Community Health Improvement Plan (CHIP)

| Who? | What? | By When? |
| --- | --- | --- |
| Steering | Review CHA | 7/31/12 |
| Steering Robin | Prioritize and select focus areas Use prioritization tools | 8/31/12 |
| Steering | Create community action plans Create task forces | 9/30/12 |
| Robin | Write Community Health Improvement Plan | 11/30/12 |
| Task Forces | Start Implementing plan Use task forces | 12/31/12 |
| Robin Task Forces | Evaluate plan progress Report progress to BOHAC | Ongoing Ongoing |
| Robin Steering Sarah | Distribute plan Printing Distribution plan | 12/31/12 |