**Community Health Assessment Deliverables**

June 2, 2017

* Final Steering Committee List
* Draft Workplan & Timeline
* Draft Budget

July 2, 2017

* Steering Committee Meeting Held
* Final Steering Committee Charter
* Final Workplan & Timeline
* Final Budget

August 2, 2017

* Visioning Plan
* Vision Statement for a Healthy Community

November 2, 2017

* Forces of Change Assessment: Threats and Opportunities Report

December 2, 2017

* Local Public Health System Assessment: Challenges and Opportunities Report

January 2, 2018

* Community Themes and Strengths Assessment: Challenges and Opportunities Report
	+ Summary of focus groups and survey
* Community Health Status Assessment
	+ Health Profile Report
	+ System for monitoring data
	+ Challenges and Opportunities Report

April 2, 2018

* 10 Priority Health Issues Report

May 2, 2018

* Goals and Strategies Report
* Draft Planning Report

September 2, 2018

* Action Plans Report
* Final CHA Released and Distributed